MARLDEN PANEL PRODUCTS LTD

DriveTec Support Day Position

Line 2 MCC VFD Upgrade — PROJ-L2VFD-2026

| Agreement | Supply and Commissioning Support Agreement DTX-SSA-2026-118 dated 04/20/2026 — DriveTec Systems GmbH / Marlden Panel Products Ltd |
| --- | --- |
| Statement answered | Support and Consignment Statement DTX-SS-2026-0442 dated 07/20/2026 (A. Petrossian), issued under clause 6.3 |
| Position stated at | Close of 08/06/2026 |
| Prepared by | R. James, Lead Electrical Engineer — Purchaser's representative under DTX-SSA-2026-118 |
| Date | 08/07/2026 |
| Contents | Section 1 — Response to the statement, with the position on the Support Days (for issue to DriveTec) Section 2 — Note to Amara Petrossian, calling off 08/10–08/14/2026 (for issue by e-mail before 16:00 UK today) Section 3 — File note (internal — not for issue) |
| Figures | Exclusive of VAT. Schedule 2 rates: Support Day £890; Saturday, Sunday or Scottish public holiday £1,335 (1.5 × £890); consignment spare holding charge £45 per calendar day. |

# Section 1 — Response to Statement DTX-SS-2026-0442, with the position on the Support Days

| To | DriveTec Systems GmbH — for the attention of A. Petrossian, VFD Vendor Project Engineer |
| --- | --- |
| From | Marlden Panel Products Ltd — R. James, Lead Electrical Engineer (Purchaser's representative) |
| Date | 08/07/2026 |
| Subject | Support and Consignment Statement DTX-SS-2026-0442 of 07/20/2026 — Agreement DTX-SSA-2026-118, clause 6.3 |

Marlden does not agree the statement as issued. Our position on each Part, and on the Support Days at the close of 08/06/2026, is set out below. All figures are exclusive of VAT.

## 1.1  Summary

| Part | Statement | Marlden | Clause |
| --- | --- | --- | --- |
| A — Support Days consumed to 07/20/2026 | 5 consumed; nil remaining | 0 consumed; 5 remaining; £0 | 4.2 |
| B — Commissioning support, on-call window 08/05–08/14/2026 | 8 days × £890 = £7,120 | £0 | 4.1, 4.2, 4.3 |
| C — Consignment spare DTX-60, holding charge 07/13–07/20/2026 | 7 days × £45 = £315 | £0 | 3.3, Sch. 2 |
| Total anticipated, Parts B and C | £7,435 | £0 |  |

## 1.2  Position on the Support Days at the close of 08/06/2026

|  | Support Days | £ |
| --- | --- | --- |
| Included in the Contract Price (clause 4.2) | 5 | — |
| Consumed by the RFI answers listed in Part A | 0 | £0 |
| Consumed on Wednesday 08/05/2026 | 0 | £0 |
| Consumed on Thursday 08/06/2026 | 0 | £0 |
| Consumed at the close of 08/06/2026 | 0 | £0 |
| Included Support Days remaining at the close of 08/06/2026 | 5 | — |
| Consignment spare holding charge to the close of 08/06/2026 | — | £0 |

At the close of 08/06/2026 none of the five included Support Days has been consumed, and the support window has cost Marlden nothing.

Under clause 4.2 a Support Day is a day of commissioning support that the Purchaser has called off in writing to the Vendor's project engineer, identifying the date and the scope of the support required, before the day on which it is provided. Marlden had called off no Support Day up to the close of 08/06/2026.

DriveTec's remote support log DTX-RS-2026-0311 records exchanges with site on 08/05 and 08/06. On each day the support was asked for by telephone, on the day, by Callan Whitmore of Ravenscar Commissioning Services, Marlden's commissioning contractor, and the log gives the support mode as “per the contractor schedule”. That schedule (Ravenscar, Rev C, 07/09/2026) is Ravenscar's programme and was circulated to DriveTec for information. Its entry placing you on call from 08/05 to 08/14 records when you were to be available; it calls off no day, and it is not a call-off by Marlden. Neither 08/05 nor 08/06 is therefore a Support Day: neither consumes an included day and neither is chargeable.

We are grateful for your help on both days. The window opened without a call-off from Marlden; our e-mail of today calls off the rest of it (see Part B below).

## 1.3  Part A — Support Days consumed to date: not agreed. 0 consumed; 5 remaining

Each of the four items is a Marlden request for information answered by DriveTec (Line 2 RFI log):

| Ref | Subject | Raised | DriveTec answer | Support Days |
| --- | --- | --- | --- | --- |
| RFI-005 | Recommended drive spares holding | 06/11/2026 (T. Hollis) | 06/15/2026 | 0 (statement: 2) |
| RFI-009 | Drive firmware revision | 06/20/2026 (F. Machar) | 06/23/2026 | 0 (statement: 1) |
| RFI-011 | Gland plate cut-outs Section A | 06/22/2026 (D. Fenwick) | 06/25/2026 | 0 (statement: 1) |
| RFI-031 | EMC filter placement | 07/13/2026 (D. Fenwick) | Outstanding | 0 (statement: 1) |
| Total |  |  |  | 0 (statement: 5) |

Clause 4.2 provides that technical responses given in answering the Purchaser's requests for information are not commissioning support: they consume no Support Day and are not chargeable. None of the five included Support Days had been consumed at 07/20/2026 and the allowance was not exhausted. (A Support Day is in any event a day under clause 4.3; RFI-005 is entered at two days for an answer given on one date.)

The same applies to the RFIs still with DriveTec — RFI-022, RFI-028 and RFI-031 — and to the written response from Applications Engineering on the F.203 events of 08/06/2026 on drive DR-L2-REF-01 (S/N DTX60-2026-04477). None of these is a Support Day.

## 1.4  Part B — Commissioning support anticipated: not agreed. £0

The statement prices the on-call window as eight chargeable days. Being on call is the availability of the project engineer that DriveTec provides under clause 4.1 within the Contract Price; it is not a Support Day. Under clause 4.2 a Support Day arises only on a date Marlden calls off in writing before the day, and the first five Support Days are included in the Contract Price. The eight Business Days in the window stand as follows:

| Date | Business Days | Called off by Marlden | Support Days | Chargeable | £ |
| --- | --- | --- | --- | --- | --- |
| Wed 08/05 – Thu 08/06/2026 | 2 | No | 0 | 0 | £0 |
| Fri 08/07/2026 | 1 | No — a call-off must precede the day | 0 | 0 | £0 |
| Mon 08/10 – Fri 08/14/2026 | 5 | Yes — Marlden e-mail of 08/07/2026 | 5 (the five included) | 0 | £0 |
| Window 08/05–08/14/2026 | 8 |  | 5 | 0 | £0 |

Part B is agreed at £0. Any further Support Day needs a separate written call-off from Marlden before the day. With the five included days called off for 08/10–08/14, a further day would be chargeable at £890 (Schedule 2), and support on a Saturday, Sunday or Scottish public holiday at £1,335 whether or not an included day remains (clause 4.3). Marlden has not called off any such day.

## 1.5  Part C — Consignment spare: not agreed. £0

Under clause 3.3 and Schedule 2 the holding charge accrues per calendar day only from the Purchaser's written storage confirmation, not from delivery. Marlden has not given that confirmation, so no holding charge accrued to 07/20/2026 and none has accrued since. Marlden will give the confirmation in writing, identifying the store and the conditions held there as Schedule 1 requires, once the storage arrangements are confirmed against Schedule 1; the charge of £45 per calendar day runs from that date.

## 1.6  Requested action

Marlden does not agree Parts A to C as issued. They are agreed at the figures in 1.1: Part A, 0 Support Days consumed; Part B, £0; Part C, £0.

No purchase order is raised, as nothing is chargeable.

Please do not invoice on DTX-SS-2026-0442 (clause 6.3). On this position there is nothing to invoice under clause 6.1 for July or for August to date.

Please re-issue the statement on this basis.

R. James

Lead Electrical Engineer, for and on behalf of Marlden Panel Products Ltd — 08/07/2026

# Section 2 — Note to Amara Petrossian

Send by e-mail from red.james@marlden-panels.example before 16:00 UK time (17:00 CEST) on Friday 08/07/2026, with Section 1 attached as a PDF. Under clause 7.2 an e-mail sent before 17:00 on a Business Day is received that day. Sent later, it is received on Monday 08/10 — and Monday would then not be called off in advance. 16:00 UK keeps it inside 17:00 on either side's clock.

| To | Amara Petrossian <amara.petrossian@drivetec-systems.example> |
| --- | --- |
| Cc | Callan Whitmore <c.whitmore@ravenscar-commissioning.example>; Grainne Sutcliffe <grainne.sutcliffe@marlden-panels.example> |
| Subject | DTX-SSA-2026-118 — Call-off of Support Days 08/10–08/14/2026, and response to statement DTX-SS-2026-0442 |
| Attachment | Marlden response to DTX-SS-2026-0442, 08/07/2026 |

Amara,

Thank you for your statement of 07/20, and for your help with site on 08/05 and 08/06. I'm sorry the reply has taken until today. This e-mail calls off your support for next week under clauses 4.2 and 7.1 of the agreement; our response to the statement is attached.

1. Call-off

I call off the following five Support Days:

| Date | Planned focus |
| --- | --- |
| Monday 08/10/2026 | Refiner drive DR-L2-REF-01 (DTX-60, S/N DTX60-2026-04477, MCC Section C, C3): motor data entry and stationary auto-tune to DTX-CMG-2025-03, taking account of your Applications Engineering review of the 08/06 F.203 events. |
| Tuesday 08/11/2026 | Refiner drive DR-L2-REF-01 as needed; preparation of the remaining drives. |
| Wednesday 08/12/2026 | Remaining Line 2 drives (Ravenscar schedule Rev C, M2–M13): nameplate entry and auto-tune, one drive per slot. |
| Thursday 08/13/2026 | Remaining Line 2 drives, continued. |
| Friday 08/14/2026 | Remaining Line 2 drives, completed; toolkit exports for the as-set parameter record, for the 08/14 parameterisation-complete milestone. |

Scope on every one of those dates, whatever the planned focus: remote commissioning support by telephone and e-mail (no site attendance) on the parameterisation and auto-tune of the Line 2 DTX-45 and DTX-60 drives to DTX-CMG-2025-03, including any fault codes that arise, available throughout the site working day (07:00–17:00 UK time; 08:00–18:00 CEST). Callan Whitmore (+44 (0)7833 902744), Priya Nandwani (+44 (0)1387 552217) and Fiona Machar (+44 (0)1387 552224) may call on you directly on those dates.

These are the five Support Days included in the Contract Price; none is chargeable. Each date counts as one Support Day whether or not the whole day is used (clause 4.3).

2. Outside the call-off

Nothing is called off for today, 08/07 (a call-off has to precede the day), for Saturday 08/08 or Sunday 08/09, or for any date after 08/14.

Ravenscar's schedule is not a call-off, and a telephone or e-mail request from site is not a call-off. Only a written call-off from me counts. If another day is needed I will call it off in writing before the day; it would be chargeable at £890, or £1,335 at a weekend or Scottish public holiday.

Your Applications Engineering response on the 08/06 F.203 events, and your answers to RFI-022, RFI-028 and RFI-031, are technical responses: they need no call-off and consume no Support Day (clause 4.2). Please send the F.203 response to me and to Callan.

3. Your statement (detail in the attached response)

Part A: 0 Support Days consumed, not 5. The four items are RFI answers, which consume no Support Day and are not chargeable (clause 4.2). The support on 08/05 and 08/06 was not called off by Marlden, so it consumed none of the five either: all five remained at the close of 08/06, and they are the five called off above.

Part B: £0, not £7,120. Being on call is not a Support Day; the only Support Days in the window are the five above.

Part C: £0, not £315. The holding charge runs only from our written storage confirmation (clause 3.3), which we have not yet given. I will send it once the store is confirmed against Schedule 1; the £45 a day runs from that date.

Total: £0 against £7,435. No purchase order is needed, and there is nothing to invoice for July or August to date. Please re-issue the statement on this basis.

Please confirm by return that you have this call-off and will work to it, and tell me today if any of the five dates cannot be covered.

Kind regards,

Red James

Lead Electrical Engineer — Purchaser's representative, DTX-SSA-2026-118

Marlden Panel Products Ltd · +44 (0)1387 552201 · red.james@marlden-panels.example

# Section 3 — File note (internal — not for issue)

| Subject | DriveTec support days and consignment spare — basis settled |
| --- | --- |
| By / date | R. James (x201) — 08/07/2026 |
| Project | Line 2 VFD Upgrade, PROJ-L2VFD-2026 — DriveTec agreement DTX-SSA-2026-118 |
| Supersedes | My working note of 07/21/2026, which took Part A at face value, leant towards a PO for Part B and treated the Part C charge as running. None of that stands. |
| Records relied on | DTX-SSA-2026-118 cl. 1.1, 3.3, 4.1–4.3, 5.3, 6.1, 6.3, 7.1–7.2, Sch. 1–2; statement DTX-SS-2026-0442 (07/20); DriveTec log DTX-RS-2026-0311 (copy 08/06 16:05); Ravenscar schedule Rev C (07/09); Line 2 RFI log (07/14); refiner drive export 08/06 10:21; project plan Rev B, R3. |

## Basis

1.	A Support Day is a date that I, as Purchaser's representative, call off in writing (e-mail) to Amara before the day, stating the date and the scope (cl. 4.2, 7.1). Nothing else uses one of the five or costs anything: not RFI answers (cl. 4.2); not the on-call line in Ravenscar's schedule; not help Amara gives on a phone or e-mail request from site; and receiving her daily log copy does not turn that help into a call-off.

2.	Each date called off counts as one Support Day whether or not the whole day is taken up (cl. 4.3), and we treat it as used even if site never rings. We call off the dates we want covered, and only those.

3.	Saturday, Sunday and Scottish public holiday support is £1,335 a day whether or not an included day remains (cl. 4.3).

4.	The consignment spare carries no holding charge until our written storage confirmation (cl. 3.3, Sch. 2), and cannot be drawn into service until then.

## Position at the close of 08/06/2026

0 of 5 Support Days consumed; 5 remaining. Window cost to that point: £0. Holding charge: £0.

On 08/05 and 08/06 Callan rang Amara on the day, on the strength of Ravenscar's Rev C schedule, which went to her for information. Nothing went to her from me, so neither day is a Support Day.

## Statement DTX-SS-2026-0442 — answered 08/07/2026

| Part | DriveTec | Agreed |
| --- | --- | --- |
| A — Support Days consumed | 5 consumed; nil remaining | 0 consumed; 5 remaining |
| B — On-call window 08/05–08/14 | £7,120 | £0 |
| C — Spare holding charge | £315 | £0 |
| Total B + C | £7,435 | £0 |

## Call-off for the rest of the window

Goes to Amara by e-mail before 16:00 UK (17:00 CEST) on 08/07, so it is received today (cl. 7.2) and is in advance of Monday. Copied to Callan and Grainne.

Mon 08/10 – Fri 08/14: five Support Days, the five included. £0.

All five are called off because the parameterisation fortnight is on the critical path with no slack (project plan R3). The refiner drive is stopped with F.203 open, and its 08/06 export still holds the factory-template motor data (P1.01 30 kW, P1.02 58 A against the 22 kW / 42 A nameplate), so a repeat motor-data entry and auto-tune is likely early in the week; the remaining drives tune from 08/12 to the 08/14 milestone. A day without Amara in that week costs more than a day of hers.

Not covered: today (a call-off cannot be made on the day), the weekend, and anything after 08/14.

## Purchase order

No PO. Nothing is payable on the statement or for the window. Grainne to be told the PO is not needed.

From 08/15 no included days remain. Any further support day (for example a refiner re-tune after the motor decision, or support at the 08/28 functional commissioning) is £890 a Business Day or £1,335 at a weekend or public holiday: PO through Grainne first, then my written call-off before the day.

## Consignment spare (Part C)

No storage confirmation given. RFI-033 (T. Hollis, 07/14 — holding location and humidity control) is still open with me. We have to store the spare to Schedule 1 now whether or not we have confirmed it, so RFI-033 closes this week.

The cl. 3.3 confirmation goes to Amara only when the store meets Schedule 1 (dry, weather-protected, 5–40 °C, RH below 60 % non-condensing, off the floor, dust-protected; humidity control where the store does not hold that) and it must name the store and the conditions held. The £45 per calendar day starts on that date. Until then the spare cannot be drawn into service, which matters while the refiner DTX-60 fault is with DriveTec.

## Not part of this position

Nothing sent to Amara today is a warranty claim. A claim on DTX60-2026-04477 goes in writing to DriveTec's warranty administration at Warwick (cl. 5.3), with the serial number, date and circumstances, and the event log, within ten Business Days of 08/06, i.e. by 08/20/2026. Her support log is not that claim.

## Actions

| # | Action | Owner | By |
| --- | --- | --- | --- |
| 1 | Send Section 2 with Section 1 attached; file the sent e-mail and Amara's acknowledgement with this note. | RJ | 08/07, 16:00 UK |
| 2 | Brief Callan: Amara is called off 08/10–08/14 only; only RJ calls off; no weekend support without RJ's written call-off and a PO. | RJ | 08/07 |
| 3 | Tell Grainne no PO is needed. | RJ | 08/07 |
| 4 | Close RFI-033; give the cl. 3.3 confirmation once the store meets Schedule 1. | RJ / T. Hollis | 08/14 |
| 5 | If any support is needed from Monday 08/17: PO first, then call-off e-mailed before 16:00 UK on 08/14. | RJ | 08/14 |