TURNPIKE CHEMICALS LLC — LAKE CHARLES COMPLEX

MEMORANDUM

Mechanical Integrity — fitness-for-service record review

| To | Steven Lee, Engineering Manager |
| --- | --- |
| Cc | James Merchant, Mechanical Integrity Engineer; Steve David, API 653 Inspector (Cert. No. 653-38472, valid to 02/20/2029); Leona Cartwright, Engineering Administrator (FFS register) |
| From | Mechanical integrity — independent review of the T-01-002 fitness-for-service record |
| Date | 06/15/2026 (record assessed as it stands on this date) |
| Subject | T-01-002 (Bund 1, heavy derivative bottoms) — the disposition the fitness-for-service record supports |
| Record reviewed | TC-MECH-FFS-0095 Rev 1, Fitness-for-Service Assessment — T-01-002, issued 11/20/2025 (prepared by Merrowfield Inspection Services, LLC; reviewed and accepted by S. David) |
| Governing basis | API 579-1/ASME FFS-1 Part 4; API 653; TC-MECH-PROC-0007 Rev 2 (issued 06/03/2026) |
| Appendices | A — Course 1 readings by survey basis, carried to 06/15/2026; B — Check against TC-MECH-PROC-0007 Rev 2 §4; C — Inputs a further assessment needs; D — Chronology to 06/15/2026 |
| Status | Record review for Engineering Manager decision. This memo is not itself a fitness-for-service assessment and carries no API 653 certification. |

DISPOSITION — NOT FIT FOR CONTINUED SERVICE: REMOVE T-01-002 FROM SERVICE On the record as it stands at 06/15/2026, T-01-002 is not fit for continued service. Stop receipts, empty and isolate the tank now, and hold it out of service. It returns to service only when (1) shell course 1 has been repaired under API 653 Section 9 to a design based on a Level 2 assessment that meets TC-MECH-PROC-0007 Rev 2, including a shell-stability check at the current 70 m/s site wind basis; (2) the repair has been inspected and accepted by a currently certified API 653 inspector; and (3) the Engineering Manager has signed the return-to-service basis and the operating envelope that goes with it. Decision required: Engineering Manager signature on this disposition under TC-MECH-PROG-0001 §6.4, by 06/19/2026.

# 1.  Purpose, scope and conventions

TC-MECH-FFS-0095 Rev 1 records a minimum measured thickness of 0.196 in on shell course 1 of T-01-002 against an acceptance criterion of 0.225 in, concludes that the tank "does not meet the acceptance criteria", answers "No" to "Fit for continued service", and refers the finding to the mechanical integrity engineer. That was on 11/20/2025. The tank is still in service (Tank Service Summary TC-PROC-REG-0007, 06/10/2026) and the record holds no disposition of the finding. This memo assesses the record as it stands at 06/15/2026, establishes the disposition it supports, and sets out what is needed before the GPSOA submission due 08/10/2026 (Notice of Findings GPSOA-2025-0417-NOF, actions A-01 and A-02).

The review covers the T-01-002 tank file, the assessments on file for the neighbouring T-01-001, the site FFS guidance, the MI written program, the 2026 tank inspection program, the FFS tracker, the corrosion-rate workbook and the two 2025 contractor UT survey workbooks, with the construction, wind, certification, process, repair, project and compliance records they cross-refer to (Section 6). The only calculations added are the carry-forward of each course 1 grid at its own rate to 06/15/2026 (Appendix A) and an indicative API 653 minimum-thickness check, used solely to test whether the acceptance criterion applied can be reproduced from the record.

Conventions

Thickness in inches (in) to three decimals; corrosion rate in mils per year (mpy) to two decimals; remaining life in years (yr) to one decimal. Dates are MM/DD/YYYY; where a source gives only a month or a year it is shown at that precision and no day is inferred.

Rate at a grid = (baseline − reading) ÷ 6.0 yr, the 04/2019 to 04/2025 interval used in the corrosion-rate workbook TC-MECH-CALC-0075 Rev 1. Course 1 reading date 04/11/2025 (TC-MECH-CALC-0075; survey range 04/10/2025–04/14/2025). Carry-forward to 06/15/2026 is 430 days (1.177 yr at 365.25 days per year).

"Below the criterion" means less than 0.225 in, the criterion applied in TC-MECH-FFS-0095 Rev 1. Using it here to count grids is not an endorsement of its value (Section 3, item N2).

# 2.  Disposition and the reasons for it

The record supports one disposition: T-01-002 is not fit for continued service and must be taken out of service. Four findings carry it.

1.	The only assessment on file says "not fit", and nothing has displaced it. Since 11/20/2025 there has been no Level 2 assessment, no repair, no rerating, no re-survey and no Engineering Manager decision under TC-MECH-PROG-0001 §6.4. The inspection plan issued two weeks later (TC-MECH-PLAN-0082 Rev 1, 12/04/2025) instead schedules the next UT survey for 04/2030 and the next internal inspection for 2029, as though the tank had passed.

2.	The shell has kept losing metal. Carried forward at each grid's own 2019–2025 rate, course 1 at 06/15/2026 has 5 of 16 grid readings below 0.225 in (4 when surveyed) and 8 of 16 on the §6.3 anomaly-scan basis (5 when surveyed). C1-E-18 crossed the criterion on 01/28/2026. The lowest values are now 0.187 in (grid) and 0.180 in (scan), both at C1-E-6. The loss is circumferential, not a single pit: all four quadrants were below 0.225 in at the 6 in elevation when surveyed.

3.	The acceptance criterion is not shown to be conservative. The 0.225 in figure cannot be reproduced from the record: its calculation sheet is not on file and the specific gravity, fill height and allowable stress behind it are not stated. An indicative API 653 §4.3.3.1 whole-course check on the record's own inputs (SG 0.96) gives 0.418 in at the 44 ft maximum fill and 0.302 in at the 32 ft normal fill; on the same formula 0.225 in corresponds to a liquid level of about 24 ft. Course 1's mean grid thickness was 0.264 in when surveyed and projects to 0.253 in at 06/15/2026. The record holds no calculation that supports continued operation at any fill height.

4.	The assessment's deficiencies weaken the file, not the finding. Of the eight inputs TC-MECH-PROC-0007 Rev 2 §4 requires on the face of an assessment, three are missing, three are incomplete, and the two that are recorded carry citation defects (Appendix B). A negative conclusion does not depend on those inputs; a positive one would. They do mean the file cannot go to GPSOA as it stands.

Table 1 — Key figures, as at 06/15/2026

| Quantity | Value | Source |
| --- | --- | --- |
| Governing reading, as surveyed | 0.196 in — §6.3 anomaly-scan minimum at C1-E-6 (3 in offset toward S), 04/11/2025 | MIS-RPT-2025-TC-LC-01, T-01-002 sheet |
| Lowest grid-point reading | 0.202 in at C1-E-6 (6 in above top of ringwall) | MIS-RPT-2025-TC-LC-01 |
| Acceptance criterion applied | 0.225 in (derivation not on file) | TC-MECH-FFS-0095 Rev 1 §3 |
| Course 1 grids below criterion — grid basis | 4 of 16 as surveyed; 5 of 16 at 06/15/2026 | Appendix A |
| Course 1 grids below criterion — §6.3 basis | 5 of 16 as surveyed; 8 of 16 at 06/15/2026 | Appendix A |
| Minimum at 06/15/2026 — grid / §6.3 basis | 0.187 in / 0.180 in (both at C1-E-6) | Appendix A |
| Crossings, 04/11/2025 to 06/15/2026 | Grid basis: C1-E-18 on 01/28/2026 §6.3 basis: C1-S-18 on 06/13/2025; C1-W-18 on 08/14/2025; C1-N-18 on 11/19/2025 | Appendix A |
| Course 1 corrosion rates, 04/2019–04/2025 | 6.17–12.67 mpy (grid); 11.50–13.67 mpy (§6.3) | Appendix A; TC-MECH-CALC-0075 Rev 1 |
| Remaining life to criterion at the governing grid | Nil — below the criterion when surveyed | Appendix A |
| Course 1 mean grid thickness / coefficient of variation | 0.264 in / 16 % as surveyed; 0.253 in carried to 06/15/2026 | Appendix A |
| Corrosion rate and remaining life on the face of the FFS | None — "No prior baseline is applied in this assessment" | TC-MECH-FFS-0095 Rev 1 §2 |
| Site design wind speed — used in 11/2025 / governing now | 45 m/s (CB-LC-2023-WIND-01) / 70 m/s (TC-CIV-WIND-0045, from 01/22/2026) | TC-MECH-TRK-0002; TC-CIV-WIND-0045 |
| Next inspection scheduled by the plan on file | Routine external visual 09/2026; internal inspection 2029 (target Q2); UT re-survey 04/2030 | TC-MECH-PLAN-0082 Rev 1 |

# 3.  What the assessment on file establishes, and what it does not

Table 2 lists what TC-MECH-FFS-0095 Rev 1 establishes; Table 3 what it does not. Appendix B checks the assessment input by input against TC-MECH-PROC-0007 Rev 2 §4.

Table 2 — What TC-MECH-FFS-0095 Rev 1 establishes

| # | Established | Record |
| --- | --- | --- |
| E1 | Course 1 governs, and its minimum reading (0.196 in) is below the 0.225 in criterion the assessment applied. The tank does not meet that criterion and is recorded as not fit for continued service. | TC-MECH-FFS-0095 Rev 1 §3, §5; MIS-RPT-2025-TC-LC-01 |
| E2 | The conclusion carries a valid API 653 certification: S. David signed on 11/20/2025, inside the validity of certificate 653-38472 (then to 11/30/2025). | TC-MECH-FFS-0095 Rev 1 §7; API certificate record (issued 02/20/2026) |
| E3 | The finding is not a single-pit artefact. On the grid basis all four readings at 6 in (0.202–0.219 in) are below the criterion; courses 1 and 2 show generalized loss, with pitting to 0.048 in below adjacent metal near the shell-to-bottom weld. | MIS-RPT-2025-TC-LC-01 (sheet note); TC-MECH-INSP-0118 Rev 1 §4, F-02, F-03 |
| E4 | Fixed inputs that are correct: construction code API 650, 6th Edition (1978); in-service code API 653; course 1 nominal 0.500 in; 28 m × 14.6 m, six courses. | CBC-ENG-TANK-CONS-BUND12 (08/14/2019); TC-MECH-REG-0011 Rev 1 |
| E5 | The triggering event, external inspection TC-MECH-INSP-0118 Rev 1, is cross-referenced. | TC-MECH-FFS-0095 Rev 1 §1 |

Table 3 — What TC-MECH-FFS-0095 Rev 1 does not establish

| # | Not established | Why it matters | Record |
| --- | --- | --- | --- |
| N1 | An assessment level, or an API 579-1 procedure. No level is named. The method compares one anomaly-scan pit minimum with the criterion. Part 4 assesses average and minimum thickness separately and, where point readings vary by more than 10 % (coefficient of variation), directs the assessor to thickness profiles; course 1's COV is 16 %, so profiles are needed, with Parts 5 and 6 for the local and pitting damage. | The record is neither a valid Level 1 nor a Level 2; it is a comparison, so its "fail" is not itself a code result (see Section 4). | TC-MECH-FFS-0095 §3; TC-MECH-PROC-0007 Rev 2 §6; Appendix A |
| N2 | A traceable acceptance criterion. The derivation (MIS-CALC-T01002-2025-01) is "not reproduced" and is not on file. The specific gravity (0.92 design or 0.96 current), fill height, plate material and joint efficiency are not stated. Indicative API 653 §4.3.3.1 whole-course values on the record's inputs (D 92 ft; S 23,600 psi, the Table 4.1 value for unknown material; E 1.0): 0.418 in (44 ft, SG 0.96); 0.401 in (44 ft, SG 0.92); 0.302 in (32 ft, SG 0.96); 0.289 in (32 ft, SG 0.92); about 5 % lower if the plate proves to be A36. 0.225 in corresponds to a liquid level of 24.1–25.1 ft. | The criterion is not shown to be conservative; the shortfall is probably larger than recorded. No rerated fill height can be read from the record. | TC-MECH-FFS-0095 §2, §3; TC-PROC-DS-0102 Rev 1; TC-MECH-REG-0011 Rev 1 |
| N3 | A corrosion rate, remaining life or interval basis. "No prior baseline is applied." The inspection report left the rate to the MI engineer, to be set on a reconciled 2019 baseline. The corrosion-rate workbook (TC-MECH-CALC-0075 Rev 1) lists per-grid rates from CB-UT-2019-012, about twice the lifetime average from nominal (C1-E-6: 12.67 vs 6.68 mpy), but the baseline has not been reconciled and no rate has been applied to the assessment. The 2016, 2020 and 2022 surveys are not on file, so no short-term rate after the 02/2024 temperature-band change (MOC-2024-003) can be computed. The 2019 survey is indexed as courses 1–3 only, yet the workbook carries 04/2019 baselines for courses 4–6. | No future corrosion allowance and no basis for any interval; the plan's 5-year UT interval has no foundation. | TC-MECH-FFS-0095 §2; TC-MECH-INSP-0118 §5; TC-MECH-CALC-0075 Rev 1; Legacy Index 2016–2023 |
| N4 | A current design loading basis. The face states neither wind speed nor study. The stability check (MIS-CALC-T01002-2025-02, not on file) used the speed "of record" on 11/20/2025: 45 m/s (CB-LC-2023-WIND-01). TC-CIV-WIND-0045 has governed since 01/22/2026 at 70 m/s; velocity pressure scales with the square of speed, so the current basis is about 2.4 times the load checked. The tank has no intermediate wind girder. | Stability with course 1 at 0.180–0.187 in has not been checked on the governing basis, including the empty-tank case. | TC-MECH-FFS-0095 §4; TC-CIV-WIND-0045; AG-CR-0182 Rev 1; TC-MECH-TRK-0002 |
| N5 | A certified, consistent source for the governing input. The FFS takes 0.196 in from TC-MECH-INSP-0118 Rev 1, signed only by an ASNT Level II technician with no API certification and no reviewer ("Reviewed by: —"): not certified evidence under TC-MECH-PROG-0001 §3. Its narrative (216 stations; lowest readings north/north-west at +0.3 to +1.2 m) does not match the workbook (40 locations; lowest at C1-E-6, 6 in). The governing survey MIS-RPT-2025-TC-LC-01 is not cited. | The value itself is sound (it is in the Level III-signed workbook) but the citation chain will not stand in a regulator's file. | TC-MECH-INSP-0118 Rev 1 §4, §8; TC-MECH-QUAL-0072 Rev 3; TC-MECH-REG-0005 Rev 6 |
| N6 | The record content TC-MECH-PROC-0007 Rev 2 §6 requires: a named level, a named preparer, the reviewer's check signature (only S. David signs) and the calculation itself. | The file fails the site's own record standard. | Appendix B, Table B-2 |
| N7 | A disposition. The referral to the MI engineer was never closed. The plan, the 2026 program (TC-MECH-PROG-0014 Rev 3), SPCC Appendix C (next UT 04/2030) and the 06/10/2026 weekly meeting ("Screening report on file. No action this week.") all treat the tank as in normal service. | The tank has operated for nearly seven months against its own FFS. | TC-MECH-PLAN-0082 Rev 1; TC-MECH-PROG-0014 Rev 3; TC-HSE-SPCC-0004 App. C; TC-MECH-MIN-0079 |

# 4.  Why removal from service, and not continued or restricted operation

Under API 653 a shell course below its acceptance thickness must be repaired, rerated or shown fit by a fitness-for-service assessment. Here the assessment has been made and shows the tank not fit; there is no rerating calculation and no repair. Continued operation therefore needs a documented basis, and the record contains none.

The negative finding does not rest on the assessment's method. Because TC-MECH-FFS-0095 compares one pit-scan minimum with the criterion instead of following Part 4, its "fail" is not itself a code result, and a profile-based assessment against a 0.225 in minimum could average out the bottom band. But 0.225 in is not a demonstrated minimum: on the record's own fill heights and specific gravity the API 653 minimum is 0.289–0.418 in, and course 1's mean thickness (0.253 in at 06/15/2026) is below the lowest of those. On every thickness basis the record holds, the shell is below a defensible minimum.

Restricted operation at a reduced liquid level is not available on this record. A safe level can only come from a traceable minimum-thickness calculation, a confirmed specific gravity and plate allowable, and a corrosion allowance for the restricted period; the record holds none of these in usable form (N2, N3). The indicative check suggests that even the 32 ft normal operating level needs more wall than course 1 now has on average. For the same reason, no Level 2 outcome is likely to support return to service at a useful liquid level without repair, which is why the return-to-service conditions require one.

The loss is active and sits where hoop stress is highest. The 6 in band is losing 10.83–12.67 mpy on the grid basis and up to 13.67 mpy on the scan basis — about one mil a month — and C1-S-18 reaches the criterion on the grid basis on 08/15/2026, five days after the GPSOA deadline.

Neither the no-shutdown position recorded at the 06/03/2026 and 06/10/2026 meetings nor the Q3 2026 CAPEX window changes this. GPSOA's Notice of Findings says its decision not to issue an imminent-danger order "is not a finding that continued operation is unconditionally acceptable". The funded repair (TC-MECH-CAP-0047 Rev 1, line 02: four 600 mm × 600 mm patch plates on course 1 and one on course 2) was scoped from the inspection report, not from an assessment; four patches covering 2.4 m cannot address loss recorded all round the 6 in band of an 88 m circumference. The turnaround work list (Rev 8, 06/04/2026) carries only a recoat for this tank.

Emptying the tank makes the empty-tank wind case govern, and that case has not been checked at 70 m/s. The out-of-service plan should therefore include the empty-tank stability check and, through the hurricane season, any storm-ballast level, set by calculation (Table 4, actions 1 and 5).

# 5.  What I would do before the GPSOA submission

The submission must carry a completed, certified FFS file for T-01-002 that states the outcome and the disposition, and a rolling-program entry that matches it. Rev 1 should not be submitted as it stands, and T-01-002 should not appear in the rolling program on a five-year interval.

Table 4 — Actions

| # | Action | Owner | By | Closes |
| --- | --- | --- | --- | --- |
| 1 | Sign the disposition. Stop receipts; empty the tank (keeping the product heated for pump-out) and isolate it. Log the change of status on the MOC log (TC-MECH-PROG-0001 §6.2); notify Operations and the Site Leader. Set any storm-ballast level by calculation. | S. Lee; Operations; J. Merchant | 06/19/2026 | N7 |
| 2 | Obtain the records the file lacks: MIS-CALC-T01002-2025-01 and -02 and grid map MIS-UT-T01002-2025 (Merrowfield); CB-UT-2016-042, CB-UT-2019-012 with its datum and grid layout, CB-UT-2020-014, CB-UT-2022-019 and CB-INT-2017-006 (Cordell Bayou archive); plate specification, radiography extent and as-built thicknesses from erection file CBC-ERC-1979-14. | J. Merchant; L. Cartwright | 07/03/2026 | N2, N3; App. C |
| 3 | Re-issue the assessment as TC-MECH-FFS-0095 Rev 2 (Rev 1 marked SUPERSEDED): re-derive the minimum required thickness with stated SG, fill height, allowable stress and joint efficiency; perform and name the Level 1 screen properly (Part 4) and record its outcome, which on the record's figures cannot be satisfied; record all eight §4 inputs with sources and issue dates (Appendix B) and the disposition; add an independent check signature and S. David's certification (valid to 02/20/2029); enter it on the FFS register. | Competent preparer; J. Merchant (check); S. David (certify); L. Cartwright | 07/17/2026 | N1, N2, N5, N6, N7 |
| 4 | Correct the records that depend on the outcome: TC-MECH-PLAN-0082 (tank out of service; internal inspection at this outage; last internal 06/2017, not 2019); TC-MECH-PROG-0014 (08/04/2019 internal unsupported); SPCC Appendix C (next UT 04/2030); TC-MECH-REG-0002 (code edition 6th, not 13th); TC-MECH-TRK-0002 (45 m/s is not on the face); TC-PROC-DS-0102 (MOC-2024-003 band 140–170 °F; maximum SG); category reassessment under TC-MECH-PROG-0001 §5.2; re-issue or supersede TC-MECH-INSP-0118 with API 653 certification. | J. Merchant; S. Ali; L. Cartwright; S. David | 07/24/2026 | N3, N5, N7 |
| 5 | Issue the out-of-service inspection scope: internal inspection to API 653 §6.4; full corrosion mapping of course 1 (0–60 in, full circumference) and course 2 on the Merrowfield ringwall datum; pitting at C1-N-01 to C1-N-06 and the shell-to-bottom weld; whether the loss is internal or external. Commission the Level 2 assessment (Parts 4, 5 and 6) with preparer, independent checker and certifier named in writing, including stability at 70 m/s (empty and operating cases). | S. David; J. Merchant; Merrowfield | 07/31/2026 (scope issued); completion dated in the program | N1–N4 |
| 6 | Hold CAPEX line 02 as the repair basis until the Level 2 defines the repair extent; re-scope under API 653 §9 and add the shell repair to the turnaround list, with Engineering Manager sign-off (TC-MECH-PROG-0001 §6.4). | H. Charles; J. Merchant; S. Lee | 07/31/2026 | Section 4 |
| 7 | Submit T-01-002 to GPSOA as "FFS complete — not fit for continued service — removed from service on [date]", with the inspection, Level 2, repair and return-to-service program and S. David as the certified individual responsible, backed by the sign-off continuity arrangement required by finding F-03. | S. Lee; J. Merchant | 08/10/2026 | A-01, A-02 |

# 6.  Records relied on

Paths are relative to the engineering file share as provided for this review.

| Record | Rev / date | File | Used for |
| --- | --- | --- | --- |
| TC-MECH-FFS-0095 — FFS assessment, T-01-002 | Rev 1, 11/20/2025 | Integrity/Tanks/T-01-002/FFS_Assessment_T-01-002.pdf | The assessment reviewed (all sections) |
| MIS-RPT-2025-TC-LC-01 — Merrowfield UT survey workbook | 04/2025 issue; T-01-002 surveyed 04/10/2025–04/14/2025; Level III sign-out 04/28/2025 | Integrity/Surveys/Merrowfield_UT_Survey_2025.xlsx | Governing readings on both bases; baselines (App. A) |
| MIS-UT-003 — Merrowfield UT procedure | Rev 3, 05/12/2024 | Integrity/Procedures/Merrowfield_UT_Procedure_Rev3.pdf | Datum §5.1; reading rule §6.2; anomaly scan §6.3 |
| TC-MECH-CALC-0075 — Corrosion rate and remaining life workbook | Rev 1, 05/22/2026 | Integrity/Programme/Corrosion_Rate_Remaining_Life.xlsx | Reading date; 6.0 yr convention; rates |
| TC-MECH-INSP-0118 — External inspection report | Rev 1, 11/12/2025 | Integrity/Tanks/T-01-002/Inspection_Report_T-01-002.pdf | FFS source; findings F-01 to F-08; certification |
| TC-MECH-PLAN-0082 — Inspection plan | Rev 1, 12/04/2025 | Integrity/Tanks/T-01-002/Inspection_Plan_T-01-002.docx | What is scheduled next (App. D) |
| TC-PROC-DS-0102 — Process data sheet | Rev 1, 10/15/2024 | Integrity/Tanks/T-01-002/Process_Data_T-01-002.pdf | SG 0.96; fill 32/44 ft; 140/160 °F |
| TC-MECH-FRM-0012 — Category assessment | Rev 2 form, 11/26/2024 | Integrity/Tanks/T-01-002/TC-MECH-FRM-0012_Category_Assessment_T-01-002.docx | Category 2; service "ambient" |
| TC-MECH-FFS-0089 — FFS assessment, T-01-001 | Rev 1, 09/25/2025 | Integrity/Tanks/T-01-001/FFS_Assessment_T-01-001.pdf | Neighbour: t-min stated per course per API 653 §4.3 |
| TC-MECH-FFS-0079 — Level 2 assessment, T-01-001 (superseded) | Rev 1, 07/20/2023 | Integrity/Tanks/T-01-001/TC-MECH-FFS-0079_Level2_Assessment_2023.pdf | Site Level 2 precedent: CTP, RSF 0.947 vs RSFa 0.900 |
| TC-MECH-PROC-0007 — FFS assessment guidance | Rev 2, 06/03/2026 | Integrity/Procedures/TC-MECH-PROC-0007_FFS_Assessment_Guidance_Rev2.docx | §2.2 Level 2 data; §4 inputs; §5 roles; §6 record |
| TC-MECH-PROG-0001 — MI written program | Rev 1, 03/2025 | Integrity/Programme/TC-MECH-PROG-0001_MI_Written_Program_Rev1.docx | §3 certified evidence; §4.1; §4.2; §5.2; §6.2; §6.4 |
| TC-MECH-PROG-0014 — Tank inspection program 2026 | Rev 3, 06/10/2026 | Integrity/Programme/Tank_Inspection_Program_2026.xlsx | Action flag; last and next internal |
| TC-MECH-TRK-0002 — FFS tracker | Position 06/12/2026 | Integrity/Programme/TC-MECH-TRK-0002_FFS_Tracker.xlsx | Wind basis attributed to TC-MECH-FFS-0095 |
| TC-MECH-REG-0002 — Tank asset register | Rev 4, 05/12/2026 | Integrity/Programme/Tank_Asset_Register.xlsx | Code edition listed as 13th (conflict) |
| Legacy Inspection Report Index 2016–2023 (Cordell Bayou) | Closed 09/26/2024 | Records/Legacy/Legacy_Inspection_Index_2016_2023.xlsx | UT 2016, 2019, 2020, 2022; internal 06/2017 |
| CBC-ENG-TANK-CONS-BUND12 — Construction records, Bunds 1 and 2 | 08/14/2019 | Records/Construction/Construction_Records_Bunds_1_2.pdf | API 650 6th Ed. (1978); SG 0.92; in service 09/05/1980 |
| TC-MECH-REG-0011 — Tank design data register | Rev 1, 04/22/2026 | Records/Construction/Tank_Design_Data_Register.xlsx | Geometry; nominal thickness; stability method; 70 m/s |
| TC-CIV-WIND-0045 — Site design wind data 2024 | Issued to engineering 01/22/2026 | Design/Wind/Site_Design_Wind_Data_2024.pdf; Correspondence/EngineeringManager/…wind_data_issued.eml | 70 m/s; supersedes the 2023 study |
| CB-LC-2023-WIND-01 — Site design wind data, final 2023 | 11/17/2023 (superseded) | Design/Wind/Site_Design_Wind_Data_Final_2023.pdf | 45 m/s basis of the 11/2025 check |
| API certificates 653-38472 / 510-24817 — S. David | Issued 02/20/2026 | Admin/Certification/Certificate_SDavid_API653_510.pdf | Validity; lapse 11/30/2025–02/20/2026 |
| TC-MECH-QUAL-0072 — Qualification record, H. Seacrest | Rev 3, 04/18/2026 | Admin/Certification/Qualification_Record_HSeacrest.pdf | No API certification |
| TC-MECH-REG-0005 — Certification register | Rev 6, 06/05/2026 | Admin/Certification/Certification_Register.xlsx | Authority to certify; single API 653 holder |
| MOC log 2023–2026 (MOC-2024-003) | Raised 02/06/2024; closed 03/19/2024 | Process/MOC/MOC_Log_2023_2026.xlsx | Temperature band 140–170 °F |
| TC-PROC-REG-0007 — Tank service summary | Updated 06/10/2026 | Process/Tank_Service_Summary.xlsx | Tank in service |
| TC-MECH-REG-0008 — Tank repair register | Rev 3, 05/22/2026 | Records/Repairs/Tank_Repair_Register.xlsx | No shell repair on T-01-002 |
| TC-MECH-CAP-0047 — CAPEX 2026 Final V2 (and V1, TC-MECH-CAP-0046) | Rev 1, 03/27/2026 (V1 03/06/2026) | Projects/CAPEX/Tank_Refurbishment_CAPEX_2026_Final_V2.pptx | Line 02 patch plates, Q3 2026 |
| Turnaround 2026 work list | Rev 8, 06/04/2026 | Projects/Turnaround/Turnaround_2026_Work_List_Rev8.xlsx | No shell repair for T-01-002 |
| AG-CR-0182 — Ashgrove tank condition review | Rev 1, 04/15/2026 | Integrity/Surveys/Ashgrove_Tank_Condition_Review_2026.pdf | Wind girders; weld details |
| GPSOA-2025-0417 audit report and -NOF Notice of Findings | 12/02/2025 | Compliance/GPSOA/ | Deadline; A-01, A-02; F-03 |
| TC-MECH-RESP-0021 — Draft GPSOA response plan | Rev B (draft), 06/12/2026 | Compliance/GPSOA/Draft_GPSOA_Response_Plan_RevB.docx | Dispositions "to be determined" |
| TC-HSE-SPCC-0004 — SPCC plan, Appendix C | Rev 4 (Appendix C dated 03/2025) | Compliance/SPCC/ | UT credited; next due 04/2030 |
| TC-MECH-MIN-0079 — Engineering weekly minutes, June 2026 | Rev 0, 06/12/2026 | Meetings/Engineering_Weekly_Minutes_June2026.docx | No-shutdown position; no action on T-01-002 |
| TC-DOC-REG-0009 — Controlled standards register | Rev 2, 05/2026 | Admin/DocumentControl/TC-DOC-REG-0009_Standards_Library.xlsx | API 650 6th Ed. text not held on site |

# 7.  Decision record

Signature below records the Engineering Manager's decision on the disposition in the box on page 1 under TC-MECH-PROG-0001 §6.4, and acknowledgement by those who must act on it. It does not certify this memo as a fitness-for-service assessment.

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| Disposition approved (TC-MECH-PROG-0001 §6.4) | Steven Lee, Engineering Manager |  |  |
| Acknowledged — certifying inspector | Steve David, API 653 Cert. No. 653-38472 (valid to 02/20/2029) |  |  |
| Acknowledged — mechanical integrity | James Merchant, Mechanical Integrity Engineer |  |  |
| Informed — site leadership | Sean Collins, Site Leader |  |  |

# Appendix A — Course 1 readings on each basis the survey workbook records, carried to 06/15/2026

Source: Merrowfield UT survey workbook MIS-RPT-2025-TC-LC-01, sheet T-01-002 (campaign MIS-2025-TC-LC-01; T-01-002 surveyed 04/10/2025–04/14/2025; Level III sign-out D. J. Tarrant 04/28/2025). Elevations are inches above the top of the foundation ringwall (MIS-UT-003 Rev 3 §5.1). Baselines are the workbook's Baseline column, Cordell Bayou record CB-UT-2019-012, dated 04/2019 (day not recorded). The workbook records course 1 on two bases:

Grid basis — the recorded minimum at the grid point: the lower of two readings taken 90° apart on one footprint (MIS-UT-003 Rev 3 §6.2). Sixteen grids: four quadrants at 6, 18, 36 and 60 in.

§6.3 anomaly-scan basis — the minimum found by scanning a 6 in radius at 1 in centres around a grid point more than 10 % below the local mean (§6.3). Recorded for the eight grids at 6 and 18 in, all logged "Pitted". The position of the minimum is recorded only for C1-E-6. The eight grids at 36 and 60 in were not scanned; on this basis they carry their grid value (Table A-1) and none is below the criterion at either date.

Rate = (baseline − reading) ÷ 6.0 yr. Thickness at 06/15/2026 = reading − rate × 1.177 yr. Crossing date = 04/11/2025 + (reading − 0.225) ÷ rate. Remaining life (RL) = (thickness − 0.225) ÷ rate, to the 0.225 in criterion applied in TC-MECH-FFS-0095 Rev 1; "nil" where the thickness is already below it. Shading: red = below 0.225 in; amber = crosses between 04/11/2025 and 06/15/2026.

Table A-1 — Grid basis (recorded minimum at the grid point)

| Grid | Elev. (in) | Reading 1 (in) | Reading 2 (in) | Recorded min (in) | Baseline (in) | Baseline date | Reading date | Rate (mpy) | Below 0.225 in (as surveyed) | Carried to 06/15/2026 (in) | Below at 06/15/2026 | Crosses 0.225 in on | RL at 04/11/2025 (yr) | RL at 06/15/2026 (yr) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| C1-N-6 | 6 | 0.221 | 0.219 | 0.219 | 0.284 | 04/2019 | 04/11/2025 | 10.83 | Yes | 0.206 | Yes | — | nil | nil |
| C1-N-18 | 18 | 0.245 | 0.244 | 0.244 | 0.301 | 04/2019 | 04/11/2025 | 9.50 | No | 0.233 | No | — | 2.0 | 0.8 |
| C1-N-36 | 36 | 0.288 | 0.287 | 0.287 | 0.331 | 04/2019 | 04/11/2025 | 7.33 | No | 0.278 | No | — | 8.5 | 7.3 |
| C1-N-60 | 60 | 0.321 | 0.322 | 0.321 | 0.362 | 04/2019 | 04/11/2025 | 6.83 | No | 0.313 | No | — | 14.0 | 12.9 |
| C1-E-6 | 6 | 0.204 | 0.202 | 0.202 | 0.278 | 04/2019 | 04/11/2025 | 12.67 | Yes | 0.187 | Yes | — | nil | nil |
| C1-E-18 | 18 | 0.234 | 0.233 | 0.233 | 0.293 | 04/2019 | 04/11/2025 | 10.00 | No | 0.221 | Yes | 01/28/2026 | 0.8 | nil |
| C1-E-36 | 36 | 0.276 | 0.278 | 0.276 | 0.324 | 04/2019 | 04/11/2025 | 8.00 | No | 0.267 | No | — | 6.4 | 5.2 |
| C1-E-60 | 60 | 0.317 | 0.316 | 0.316 | 0.358 | 04/2019 | 04/11/2025 | 7.00 | No | 0.308 | No | — | 13.0 | 11.8 |
| C1-S-6 | 6 | 0.212 | 0.213 | 0.212 | 0.281 | 04/2019 | 04/11/2025 | 11.50 | Yes | 0.198 | Yes | — | nil | nil |
| C1-S-18 | 18 | 0.239 | 0.238 | 0.238 | 0.296 | 04/2019 | 04/11/2025 | 9.67 | No | 0.227 | No | — | 1.3 | 0.2 |
| C1-S-36 | 36 | 0.284 | 0.283 | 0.283 | 0.328 | 04/2019 | 04/11/2025 | 7.50 | No | 0.274 | No | — | 7.7 | 6.6 |
| C1-S-60 | 60 | 0.324 | 0.325 | 0.324 | 0.361 | 04/2019 | 04/11/2025 | 6.17 | No | 0.317 | No | — | 16.1 | 14.9 |
| C1-W-6 | 6 | 0.217 | 0.216 | 0.216 | 0.283 | 04/2019 | 04/11/2025 | 11.17 | Yes | 0.203 | Yes | — | nil | nil |
| C1-W-18 | 18 | 0.242 | 0.241 | 0.241 | 0.299 | 04/2019 | 04/11/2025 | 9.67 | No | 0.230 | No | — | 1.7 | 0.5 |
| C1-W-36 | 36 | 0.286 | 0.285 | 0.285 | 0.330 | 04/2019 | 04/11/2025 | 7.50 | No | 0.276 | No | — | 8.0 | 6.8 |
| C1-W-60 | 60 | 0.319 | 0.320 | 0.319 | 0.360 | 04/2019 | 04/11/2025 | 6.83 | No | 0.311 | No | — | 13.8 | 12.6 |

Table A-2 — §6.3 anomaly-scan basis (minimum within 6 in radius of the grid point)

| Grid | Elev. (in) | §6.3 minimum (in) | Position of minimum | Grid reading (in) | Baseline (in) | Baseline date | Reading date | Rate (mpy) | Below 0.225 in (as surveyed) | Carried to 06/15/2026 (in) | Below at 06/15/2026 | Crosses 0.225 in on | RL at 04/11/2025 (yr) | RL at 06/15/2026 (yr) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| C1-N-6 | 6 | 0.208 | not recorded | 0.219 | 0.284 | 04/2019 | 04/11/2025 | 12.67 | Yes | 0.193 | Yes | — | nil | nil |
| C1-N-18 | 18 | 0.232 | not recorded | 0.244 | 0.301 | 04/2019 | 04/11/2025 | 11.50 | No | 0.218 | Yes | 11/19/2025 | 0.6 | nil |
| C1-E-6 | 6 | 0.196 | 3 in toward S | 0.202 | 0.278 | 04/2019 | 04/11/2025 | 13.67 | Yes | 0.180 | Yes | — | nil | nil |
| C1-E-18 | 18 | 0.221 | not recorded | 0.233 | 0.293 | 04/2019 | 04/11/2025 | 12.00 | Yes | 0.207 | Yes | — | nil | nil |
| C1-S-6 | 6 | 0.203 | not recorded | 0.212 | 0.281 | 04/2019 | 04/11/2025 | 13.00 | Yes | 0.188 | Yes | — | nil | nil |
| C1-S-18 | 18 | 0.227 | not recorded | 0.238 | 0.296 | 04/2019 | 04/11/2025 | 11.50 | No | 0.213 | Yes | 06/13/2025 | 0.2 | nil |
| C1-W-6 | 6 | 0.205 | not recorded | 0.216 | 0.283 | 04/2019 | 04/11/2025 | 13.00 | Yes | 0.190 | Yes | — | nil | nil |
| C1-W-18 | 18 | 0.229 | not recorded | 0.241 | 0.299 | 04/2019 | 04/11/2025 | 11.67 | No | 0.215 | Yes | 08/14/2025 | 0.3 | nil |

Table A-3 — Summary on each basis

| Basis | Minimum as surveyed (04/11/2025) | Grids below 0.225 in (as surveyed) | Minimum at 06/15/2026 | Grids below 0.225 in (at 06/15/2026) | Crossing between those dates |
| --- | --- | --- | --- | --- | --- |
| Grid basis (16 grids) | 0.202 in at C1-E-6 | 4 of 16 — C1-N-6, C1-E-6, C1-S-6, C1-W-6 | 0.187 in at C1-E-6 | 5 of 16 — C1-N-6, C1-E-6, C1-E-18, C1-S-6, C1-W-6 | C1-E-18 on 01/28/2026 |
| §6.3 anomaly-scan basis (8 scanned grids; the other 8 carry grid values) | 0.196 in at C1-E-6 (3 in toward S) | 5 of 16 — C1-N-6, C1-E-6, C1-E-18, C1-S-6, C1-W-6 | 0.180 in at C1-E-6 | 8 of 16 — C1-N-6, C1-N-18, C1-E-6, C1-E-18, C1-S-6, C1-S-18, C1-W-6, C1-W-18 | C1-S-18 on 06/13/2025 C1-W-18 on 08/14/2025 C1-N-18 on 11/19/2025 |

Notes to Appendix A

1.  On the §6.3 basis the reading lies up to 6 in from the grid point at which the baseline was taken, so the scan-basis rate is an upper bound (as TC-MECH-CALC-0075 notes for C1-E-6). Carrying the scan minima at the grid-point rate instead moves the three crossings to C1-S-18 on 06/25/2025, C1-W-18 on 09/09/2025, C1-N-18 on 01/05/2026; the grids that cross and the count of 8 at 06/15/2026 are unchanged.

2.  Next crossings on the grid basis after 06/15/2026: C1-S-18 on 08/15/2026, C1-W-18 on 12/06/2026, C1-N-18 on 04/11/2027. C1-S-18 crosses five days after the GPSOA deadline of 08/10/2026.

3.  Course 1 mean grid thickness 0.264 in, standard deviation 0.043 in, coefficient of variation 16.2 % as surveyed; mean carried to 06/15/2026 0.253 in. Thickness falls steadily with elevation (6 in: 0.202–0.219 in; 60 in: 0.316–0.324 in), consistent with loss concentrated at the bottom of the course.

4.  The 2019–2025 rates are about twice the lifetime average from the 0.500 in nominal over 44.6 yr in service (C1-E-6: 12.67 vs 6.68 mpy). They are the highest-rate basis the record holds and are used as found. A short-term rate after the 02/2024 temperature-band change cannot be computed from the record (Appendix C).

5.  TC-MECH-INSP-0118 Rev 1 §4 reproduces the course minima of this workbook (0.196 / 0.348 / 0.321 / 0.282 / 0.289 / 0.231 in for courses 1–6). No thickness reading on T-01-002 has been taken since 04/2025.

# Appendix B — Check of TC-MECH-FFS-0095 Rev 1 against the inputs TC-MECH-PROC-0007 Rev 2 §4 requires on the face

TC-MECH-PROC-0007 Rev 2 §4: "The following inputs are always recorded on the face of the assessment", each "traceable to a named source document and its issue date". TC-MECH-FFS-0095 Rev 1 pre-dates Rev 2 (issued 06/03/2026), but any file submitted to GPSOA after that date is judged against Rev 2, the governing basis for this review.

Table B-1 — Section 4 inputs

| # | Input required on the face (§4) | Recorded? | Value on the face of TC-MECH-FFS-0095 Rev 1 | Source cited on the face | What the record holds / comment |
| --- | --- | --- | --- | --- | --- |
| 1 | Governing UT thickness survey — document number, revision, campaign date | No | Not stated. The face takes the thickness from the inspection report and cites the UT procedure. | TC-MECH-INSP-0118 Rev 1 (11/12/2025) §4; "Merrowfield UT Procedure Rev 3, Section 5" | Record: MIS-RPT-2025-TC-LC-01, 04/2025 issue (the workbook carries no revision number); campaign 04/07/2025–04/29/2025; T-01-002 surveyed 04/10/2025–04/14/2025; Level III sign-out 04/28/2025. |
| 2 | Governing UT survey contractor and campaign reference | Partly | Contractor named (Merrowfield Inspection Services, LLC, as preparer and procedure owner). Campaign reference not stated; Attachment 4 cites grid map "MIS-UT-T01002-2025". | FFS header; §2; §6 | Record: campaign MIS-2025-TC-LC-01 (workbook cover). Grid map MIS-UT-T01002-2025 is not on file. |
| 3 | Corrosion rate applied, with basis and the service interval over which it was calculated | No | None: "No prior baseline is applied in this assessment. The 2019 UT record has not been used as an input." | §2 | Record: long-term per-grid rates 04/2019–04/2025 (6.0 yr) from CB-UT-2019-012 — 13.67 mpy at C1-E-6 (§6.3) and 12.67 mpy (grid) — TC-MECH-CALC-0075 Rev 1 (05/22/2026). No short-term rate. TC-MECH-INSP-0118 §5: "Not determined". |
| 4 | Minimum required thickness, with the calculation basis cited | Partly | 0.225 in "acceptance criterion", "derived per API 579-1 / ASME FFS-1 Part 4 on the API 653 basis" from geometry and the SG input in §2. | §3; calculation sheet MIS-CALC-T01002-2025-01 ("not reproduced here") | Calculation not on file. SG not stated as a number (§2: "per TC-PROD-BOT-02"); the record holds 0.96 typical (TC-PROC-DS-0102 Rev 1, 10/15/2024) and 0.92 design (TC-MECH-REG-0011 Rev 1, 04/22/2026). Fill height, allowable stress and joint efficiency not stated. Not reproducible (Section 3, N2). |
| 5 | Design loading basis, referencing the current site design wind data study and any superseded predecessor | No | "The site design wind speed of record at the date of this assessment" — no value, no study. | §4; calculation sheet MIS-CALC-T01002-2025-02 (not on file) | At 11/20/2025: 45 m/s, CB-LC-2023-WIND-01 (11/17/2023). Current: 70 m/s, TC-CIV-WIND-0045, issued to engineering 01/22/2026, superseding it. TC-MECH-TRK-0002 lists "45 m/s" and "11/17/2023" as quoted on the face; they are not. |
| 6 | Applicable construction code edition | Yes | API 650, 6th Edition (1978) | "Construction records" (no reference or issue date) | Correct: nameplate BEF-1980-0508 in CBC-ENG-TANK-CONS-BUND12 (08/14/2019). Source not cited with reference and date. TC-MECH-REG-0002 Rev 4 (05/12/2026) wrongly lists "API 650, 13th Edition". |
| 7 | Applicable in-service code | Yes | API 653 | "MI Written Program Section 4.3" | Clause mis-cited: TC-MECH-PROG-0001 Rev 1 §4.1 sets API 653 for field-erected tanks; §4.3 covers diked storage. Revision and date not cited. |
| 8 | Governing damage mechanism and the API 579-1 Part invoked | Partly | General metal loss, shell course 1; Part 4. | Header; §1; §3 | Pitting near the shell-to-bottom weld (to 0.048 in) is "noted" but not assessed (Part 6), and the governing value is itself a pit-scan minimum. The localized lower-band loss is not considered under Part 5. |

Result: 3 not recorded (1, 3, 5); 3 recorded in part (2, 4, 8); 2 recorded (6, 7), each with a citation defect.

Table B-2 — Other record content required by TC-MECH-PROC-0007 Rev 2 §5 and §6

| Requirement | Met? | Observation |
| --- | --- | --- |
| Controlled header: number, revision, issue date, originator, checker, approver | Partly | Number, revision and date present. Originator given only as "Merrowfield Inspection Services, LLC"; no checker or approver. |
| Tank identifier, bund, service, construction code edition | Yes | T-01-002, Bund 1, heavy derivative bottoms, API 650 6th Edition (1978). |
| Assessment level named explicitly (Level I, II or III) | No | Not named. The inspection plan and the weekly minutes call it a "screening". |
| All §4 inputs traceable to a source with issue date | No | Table B-1. |
| Calculation in the body or attached by number and revision | No | Attachments 2 and 3 cited by number only; neither is on file. |
| Acceptance criterion applied and numerical result | Yes | 0.225 in against 0.196 in — criterion not traceable (N2). |
| Conclusion at the level performed | Partly | "Does not meet the acceptance criteria"; the level is not stated. |
| Certifier signature block (API 653) | Yes | S. David, 653-38472, expiry 11/30/2025, signed 11/20/2025. |
| Reviewer's check signature, independent of the preparer (§5) | No | Only S. David signs. No named preparer. |
| Cross-reference to the triggering inspection report or event | Yes | TC-MECH-INSP-0118 Rev 1 — itself not certified evidence under TC-MECH-PROG-0001 §3. |
| On the FFS register ("an assessment that is not on the register is not on file") | Partly | Listed on TC-MECH-TRK-0002 (maintained by J. Merchant). No register maintained by L. Cartwright, as §6 describes, is on file. |

# Appendix C — Inputs a further assessment would need

Inputs for the Level 2 assessment (TC-MECH-PROC-0007 Rev 2 §2.2 and §4) that must precede repair design and any return to service. "Held" = the record holds the input in usable form; "Partly" = held incompletely or with a conflict; "Not held" = the record does not hold it.

| # | Input | Value | Record and date | Held? |
| --- | --- | --- | --- | --- |
| Thickness and damage |  |  |  |  |
| C1 | Course 1 point readings (16 grids, two readings each) | Appendix A, Table A-1 | MIS-RPT-2025-TC-LC-01, T-01-002 sheet; surveyed 04/10/2025–04/14/2025 | Held |
| C2 | Anomaly-scan minima and their positions | 8 minima, 0.196–0.232 in; position recorded only at C1-E-6 (3 in toward S) | MIS-RPT-2025-TC-LC-01 | Partly |
| C3 | Critical thickness profiles (meridional and circumferential) through the thinned band, full circumference | — | 216-station grid map MIS-UT-T01002-2025 cited in TC-MECH-INSP-0118 Att. 1 and FFS Att. 4; not on file | Not held |
| C4 | Current thickness (after 04/2025) | Projections only (Appendix A) | No reading since 04/2025 | Not held |
| C5 | Pit depth, size and spacing near the shell-to-bottom weld | Depths to 0.048 in at C1-N-01 to C1-N-06; size and spacing not recorded | TC-MECH-INSP-0118 Rev 1 §4, F-03 (11/12/2025) | Partly |
| C6 | Shell-to-bottom weld and bottom/annular plate in the critical zone | — | Last internal CB-INT-2017-006 (06/2017); report not on file | Not held |
| C7 | Side (internal/external) and cause of the loss | "Consistent with under-insulation moisture ingress in the wetted band" | TC-MECH-INSP-0118 Rev 1 F-02; internal surface not examined since 06/2017 | Partly |
| Geometry, material and construction |  |  |  |  |
| C8 | Diameter, height, number of courses, course height | 28 m (92 ft); 14.6 m (48 ft); 6; 8 ft | TC-MECH-REG-0011 Rev 1 (04/22/2026); CBC-ENG-TANK-CONS-BUND12 (08/14/2019) | Held |
| C9 | Nominal course thicknesses, courses 1–6 | 0.500 / 0.437 / 0.375 / 0.312 / 0.312 / 0.250 in | TC-MECH-REG-0011 Rev 1 (04/22/2026) | Held |
| C10 | As-built course thicknesses (mill certificates) | — | Erection contract file CBC-ERC-1979-14, plant vault (not reproduced) | Not held |
| C11 | Shell plate specification, for allowable stress (API 653 Table 4.1) | — | Not recorded for T-01-002 | Not held |
| C12 | Joint efficiency and radiography extent (API 653 Table 4.2) | "Radiographed"; extent not stated | Certificate BEF-COC-1980-0508 excerpt, CBC-ENG-TANK-CONS-BUND12 (08/14/2019) | Partly |
| C13 | Construction code edition, and its text | API 650, 6th Edition (1978), Addendum 2 where applicable | CBC-ENG-TANK-CONS-BUND12; text not held on site (TC-DOC-REG-0009 Rev 2, 05/2026); register conflict (TC-MECH-REG-0002 Rev 4) | Partly |
| C14 | Shell-to-bottom weld detail | Single continuous outside fillet with intermittent inside fillet | AG-CR-0182 Rev 1 (04/15/2026); inside fillet not confirmed | Held |
| C15 | Wind girders | Primary top girder only; no intermediate girder; section properties not recorded | AG-CR-0182 Rev 1 (04/15/2026) | Partly |
| Operating and loading |  |  |  |  |
| C16 | Maximum liquid level | 44 ft maximum; 32 ft normal | TC-PROC-DS-0102 Rev 1 (10/15/2024) | Held |
| C17 | Highest specific gravity of contents | 0.96 typical; 0.92 design; maximum not recorded | TC-PROC-DS-0102 Rev 1 (10/15/2024); TC-MECH-REG-0011 Rev 1 (04/22/2026) | Partly |
| C18 | Operating temperature | 140 °F normal / 160 °F max; 140–170 °F; "ambient" | TC-PROC-DS-0102 Rev 1; MOC-2024-003 (closed 03/19/2024); TC-MECH-PLAN-0082 Rev 1 and TC-MECH-FRM-0012 | Partly (conflict) |
| C19 | Design pressure | Atmospheric; 1.5 in H2O design | TC-PROC-DS-0102 Rev 1 (10/15/2024) | Held |
| C20 | Design wind speed — current basis | 70 m/s, 3-s gust at 33 ft, Exposure C, Risk Category III, MRI 1,700 yr; Kzt 1.00 | TC-CIV-WIND-0045, issued to engineering 01/22/2026 | Held |
| C21 | Design wind speed — superseded predecessor | 45 m/s | CB-LC-2023-WIND-01 (11/17/2023) | Held |
| C22 | Foundation settlement | 12 mm differential across the diameter | TC-MECH-INSP-0118 Rev 1 F-08 (walk-around 11/09/2025) | Held |
| Corrosion rate |  |  |  |  |
| C23 | Long-term rate per grid, with interval | 6.17–12.67 mpy (grid); 11.50–13.67 mpy (§6.3); 04/2019–04/2025, 6.0 yr | CB-UT-2019-012 via MIS-RPT-2025-TC-LC-01; TC-MECH-CALC-0075 Rev 1 (05/22/2026) | Held |
| C24 | Datum and grid layout of the 2019 baseline | "2019 baseline under reconciliation" | TC-MECH-INSP-0118 Rev 1 §5 | Not held |
| C25 | Earliest UT baseline (2016) | — | CB-UT-2016-042, courses 1–3 (index entry only) | Not held |
| C26 | Short-term (post-event) rate | — | CB-UT-2020-014 and CB-UT-2022-019 (index entries only); event MOC-2024-003 | Not held |
| Acceptance |  |  |  |  |
| C27 | Minimum required thickness, with derivation | 0.225 in applied; derivation absent | TC-MECH-FFS-0095 Rev 1; MIS-CALC-T01002-2025-01 not on file | Partly |
| C28 | Shell-stability check at the current wind basis (empty and operating) | — | Method: TC-MECH-REG-0011 Rev 1 Method Notes (API 650 Annex V); 45 m/s check MIS-CALC-T01002-2025-02 not on file | Not held |
| C29 | Allowable remaining strength factor | 0.90 (site precedent) | TC-MECH-FFS-0079 Rev 1 (07/20/2023, superseded) | Held |
| C30 | Assessment period and future corrosion allowance | — | No period defined on any record | Not held |

The record does not hold 10 inputs (C3, C4, C6, C10, C11, C24, C25, C26, C28, C30) and holds 9 only in part (C2, C5, C7, C12, C13, C15, C17, C18, C27). Items C3, C6, C10, C11, C24 and C28 govern the Level 2 result and the repair design.

# Appendix D — Chronology of the records bearing on the disposition, to 06/15/2026

Entries marked "Derived" are dates calculated in Appendix A, not records.

| Date | Record | What it records | Bearing on the disposition |
| --- | --- | --- | --- |
| 09/05/1980 | CBC-ENG-TANK-CONS-BUND12 | Placed in service (hydrotest complete 08/14/1980). API 650, 6th Edition (1978); design SG 0.92; course 1 nominal 0.500 in. | Construction basis. |
| 2016 | CB-UT-2016-042 (Legacy Index) | UT survey, shell courses 1–3 (Delta Coast). | Earliest UT baseline; not on file. |
| 06/2017 | CB-INT-2017-006 (Legacy Index) | Internal inspection; tank out of service 06/2017 (Bayou NDT). | Last internal on record. Plan and program state 2019. |
| 04/2019 | CB-UT-2019-012 (Legacy Index) | UT survey, shell grid courses 1–3 (Vermilion). | Baseline for every rate; datum unconfirmed. |
| 2020 | CB-UT-2020-014 (Legacy Index) | "Post-cleaning verification grid" (Cameron Coastal). TC-PROC-DS-0102 refers to a 2020 re-baseline. | Short-term data; not on file. |
| 05/03/2020 | WO-2020-063 (TC-MECH-REG-0008) | Ringwall crack sealed, north quadrant. | Foundation history. |
| 2022 | CB-UT-2022-019 (Legacy Index) | Follow-up grid on shell course 1 (Bayou NDT). | Short-term data; not on file. |
| 08/24/2023 | WO-2023-127 (TC-MECH-REG-0008) | External recoat, courses 1–2 north face (signed off 09/06/2023). | Coating broken down again by 11/2025 (F-01). |
| 11/17/2023 | CB-LC-2023-WIND-01 | Site design wind speed 45 m/s. | Basis of the 11/2025 stability check. |
| 02/06/2024 | MOC-2024-003 | Operating temperature band widened from 145–160 °F to 140–170 °F (closed 03/19/2024). | Change inside the rate interval; not carried to data sheet, plan or category form. |
| 10/01/2024 | CB-LC-HAND-2024-01 | Site acquired from Cordell Bayou; legacy records transferred with known gaps. | Records basis. |
| 10/15/2024 | TC-PROC-DS-0102 Rev 1 | SG 0.96 typical; fill 32 ft normal / 44 ft max; 140 °F / 160 °F; "no MOC entry open". | Inputs to minimum thickness. |
| 11/26/2024 | TC-MECH-FRM-0012 | Category 2; service described as "ambient". | Takes no account of MOC-2024-003. |
| 04/10/2025– 04/14/2025 | MIS-RPT-2025-TC-LC-01 | Course 1 surveyed (readings dated 04/11/2025 in TC-MECH-CALC-0075). Governing 0.196 in (§6.3, C1-E-6); all four 6 in grids below 0.225 in. Level III sign-out 04/28/2025. | Governing data. No reading since. |
| 06/13/2025 | Derived (Table A-2) | C1-S-18 crosses 0.225 in on the §6.3 basis. | — |
| 08/14/2025 | Derived (Table A-2) | C1-W-18 crosses 0.225 in on the §6.3 basis. | — |
| 11/06/2025– 11/10/2025 | TC-MECH-INSP-0118 Rev 1 (issued 11/12/2025) | External inspection. Course minima reproduce the 04/2025 workbook. F-02 refers thinning to FFS; F-03 pitting to repair assessment. Signed by an ASNT Level II technician only. | Not certified evidence (TC-MECH-PROG-0001 §3). |
| 11/18/2025– 11/20/2025 | GPSOA-2025-0417 | GPSOA compliance audit on site. | — |
| 11/19/2025 | Derived (Table A-2) | C1-N-18 crosses 0.225 in on the §6.3 basis. | — |
| 11/20/2025 | TC-MECH-FFS-0095 Rev 1 | 0.196 in against 0.225 in; "does not meet the acceptance criteria"; "Fit for continued service: No"; referred to the MI engineer. Signed by S. David (certificate valid to 11/30/2025). | The assessment on file. |
| 11/30/2025 | API certificate 653-38472 | S. David's certificate lapses until 02/20/2026. | Single certified signatory (GPSOA F-03). |
| 12/02/2025 | GPSOA-2025-0417; -NOF | FFS on the nine critical tanks and an acceptable rolling program required by 08/10/2026. | Submission deadline. |
| 12/04/2025 | TC-MECH-PLAN-0082 Rev 1 | Plan issued: next internal 2029, UT 04/2030; reviewer S. David, inside the certificate lapse. | Plan ignores the FFS outcome. |
| 01/22/2026 | TC-CIV-WIND-0045; manager memo; transmittal | 70 m/s becomes the site basis; 2023 study superseded (MOC-2026-002, closed 02/15/2026). | Stability basis on file superseded. |
| 01/28/2026 | Derived (Table A-1) | C1-E-18 crosses 0.225 in on the grid basis. | — |
| 02/20/2026 | API certificate 653-38472 | S. David recertified, valid to 02/20/2029. | Current certifier. |
| 03/06/2026 | TC-MECH-CAP-0046 Rev 1 (CAPEX Final) | Line 02: course 1 and 2 patch plates and ringwall re-grouting, Q3 2026. | Repair not derived from an assessment. |
| 03/27/2026 | TC-MECH-CAP-0047 Rev 1 (CAPEX Final V2) | Line 02 retained; 21 working days downtime. | As above. |
| 04/15/2026 | AG-CR-0182 Rev 1 | No intermediate wind girder; shell-to-bottom and roof-to-shell details recorded. | Stability inputs. |
| 04/22/2026 | TC-MECH-REG-0011 Rev 1 | Design SG 0.92; design wind 70 m/s; stability method (API 650 Annex V). | Level 2 inputs. |
| 05/12/2026 | TC-MECH-REG-0002 Rev 4; TC-HSE-SPCC-0004 Rev 4 | Register lists API 650 13th Edition; SPCC Appendix C credits the 04/2025 UT, next due 04/2030. | Records in conflict with the outcome. |
| 05/14/2026 | TC-WO-2026-0047 | Fixed roof vent hood coating repair. | No shell work. |
| 05/15/2026 | TC-MECH-RESP-0021 Rev B (as reported) | GPSOA interim status update submitted. | — |
| 05/22/2026 | TC-MECH-CALC-0075 Rev 1 | Per-grid rates for T-01-002; remaining life at C1-E-6 not stated. | Rate data. |
| 06/03/2026 | TC-MECH-PROC-0007 Rev 2; manager memo; weekly meeting | Guidance Rev 2 issued; S. David to sign all assessments; no-shutdown position recorded. | Governing guidance. |
| 06/04/2026 | Turnaround 2026 work list Rev 8 | T-01-002: roof drain replacement and course 1–2 recoat only. | No shell repair planned. |
| 06/10/2026 | TC-MECH-PROG-0014 Rev 3; weekly meeting | Action required before 08/10/2026: Y; last internal 08/04/2019; "Screening report on file. No action this week." | Outcome not acted on. |
| 06/12/2026 | TC-MECH-TRK-0002; TC-MECH-RESP-0021 Rev B | Tracker lists 0.196 in and "45 m/s"; draft response plan leaves dispositions to be determined. | — |
| 06/15/2026 | This memo (Appendix A) | Carried forward: 5 of 16 grids below (grid basis), 8 of 16 (§6.3); minimum 0.187 / 0.180 in. | Disposition: remove from service. |

Table D-2 — What the inspection plan on file schedules next (TC-MECH-PLAN-0082 Rev 1, 12/04/2025)

| Activity | Interval | Last performed (per plan) | Next due (per plan) | Against the record |
| --- | --- | --- | --- | --- |
| External visual (routine) | 12 months | 09/2025 (Merrowfield routine round) | 09/2026 | The next dated activity. Takes no thickness measurement on course 1. |
| Internal inspection (API 653 §6.4) | 10 years | "2019 (legacy record, Cordell Bayou file)" | 2029 (target Q2) | The plan's stated "next scheduled event" (§3). The index records the last internal as 06/2017 (CB-INT-2017-006, the row the plan itself cites); TC-MECH-PROG-0014 gives 08/04/2019, which no record supports. On the plan's own 10-year interval the internal falls due 06/2027. |
| External UT re-survey | 5 years | 04/2025 | 04/2030 | Interval driver cites an "in-service short-term corrosion rate" the workbook does not hold. Remaining life is nil, so TC-MECH-PROG-0001 §4.2 cannot yield a 5-year interval. |
| Formal external (API 653 §6.3.2) | 5 years | 11/12/2025 | 11/12/2030 | Based on an inspection report that is not certified evidence. |

The plan schedules nothing for course 1 before 2029. After 06/15/2026 the dated events in the record are the GPSOA deadline (08/10/2026), the grid-basis crossing at C1-S-18 (08/15/2026, derived), the CAPEX Q3 2026 execution window and the routine external visual (09/2026).